## Sheet1
Control Category | Control ID | Control Name | Status | Maps to NIST | Evidence / Notes | Key Risks if Not Implemented | Recommended Action | Priority | Timeline
Governance | AI-G1 | AI Risk Governance Roles | Partially Implemented | Govern | Model development responsibilities are informally understood but not documented; model owner role not defined; no RACI matrix | Lack of accountability may lead to unmanaged model risk, inconsistent decisions, and certification gaps | Define RACI matrix for AI risk governance; assign model owner and risk owner roles; track approvals for major changes | High | Short (0–3 months)
Governance | AI-G2 | Model Lifecycle Documentation | Partially Implemented | Govern | Basic model metadata stored; no formal documentation of lifecycle stages or decision records | Inability to trace model decisions increases compliance risk and reduces audit readiness | Create model lifecycle documentation templates covering purpose, training data, evaluation, release, & deprecation | Medium | Medium (3–12 months)
Governance | AI-G3 | Human-in-the-Loop Oversight | Implemented | Govern / Manage | Hiring managers review recommendations before decisions; human override possible | Operational effectiveness depends on consistent use of oversight; risk if human review becomes rubber-stamping | Formalize override workflow and record justifications; track rate of automated vs overridden decisions | Medium | Medium (3–12 months)
Governance | AI-G4 | Data Lineage & Provenance | Partially Implemented | Govern / Map | Training datasets stored, but lineage between raw, cleaned and feature sets not fully tracked | Model outcomes may be challenged without ability to trace back to original datasets | Implement lineage tracking in feature store; store provenance metadata; automate lineage reporting | High | Medium (3–12 months)
Governance | AI-G5 | High-Risk System Registration | Not Implemented | Govern / Map | System not formally registered as high-risk under EU AI Act expectations; regulatory tracking absent | Misalignment with future regulatory requirements may cause remediation backlogs or penalties | Track system as high-risk; monitor EU AI Act implementation; prepare conformity documentation | High | Medium (3–12 months)
Data | AI-D1 | Dataset Quality Requirements | Partially Implemented | Map / Measure | Data quality checks exist but are manual; missing thresholds & coverage metrics | Poor data quality may distort rankings and reduce fairness | Define data quality requirements; automate quality validation in pipeline | Medium | Medium (3–12 months)
Data | AI-D2 | Bias Identification and Mitigation | Not Implemented | Map / Measure | No systematic bias testing or measurement; sensitive attribute correlations unknown | Discriminatory outcomes may violate GDPR fairness, harm candidates, and create reputational & legal risk | Implement quarterly bias assessment reports; select mitigation strategies (reweighting, resampling); document impact | High | Short (0–3 months)
Data | AI-D3 | Sensitive Attribute Handling | Partially Implemented | Map / Measure | Sensitive attributes removed at ingestion but may be inferred indirectly; monitoring absent | Unintentional bias may persist through proxy attributes | Identify proxy variables; monitor for indirect correlations; add fairness-aware preprocessing | High | Medium (3–12 months)
Model | AI-M1 | Explainability & Transparency | Partially Implemented | Govern / Manage | Model explanations generated for top recommendations but insufficient depth for audit use | Limited transparency may reduce trust and fail expectations for meaningful explanation | Produce human-readable rationale summaries; align explanation outputs with GDPR process transparency | High | Short (0–3 months)
Model | AI-M2 | Adverse Impact Monitoring | Not Implemented | Govern / Manage | No tracking of disparate impact or adverse scoring patterns over time | Harmful model outcomes may accumulate without detection | Measure adverse impact quarterly; define escalation thresholds; link to retraining triggers | High | Medium (3–12 months)
Model | AI-M3 | Model Drift Detection & Retraining | Not Implemented | Measure / Manage | No drift detection or performance degradation alarms | Degraded accuracy may negatively affect candidate rankings, reducing business value | Implement drift detection; schedule retraining cycles; define monitoring thresholds | Medium | Medium (3–12 months)
Model | AI-M4 | Model Versioning & Approval Gates | Implemented | Govern / Manage | MLflow used for versioning; basic approval documented in release notes | Lack of robust formal gating may allow unvalidated models in production | Add sign-off workflow requiring security + fairness checks before release | Medium | Medium (3–12 months)
Model | AI-M5 | Attack/Manipulation Resistance | Not Implemented | Measure / Manage | No defenses against data poisoning or adversarial manipulation | Attackers may bias rankings, elevate fraudulent candidates, or suppress strong applicants | Conduct threat modeling; implement adversarial robustness testing; add anomaly detection | High | Medium (3–12 months)
User Interaction | AI-U1 | User Dispute & Appeal Mechanisms | Not Implemented | Govern / Manage | No documented process for candidates to contest algorithmic outcomes | Violates expectations for meaningful human oversight; weakens regulatory alignment | Create applicant appeal workflow; publish contact and escalation path; track cases | High | Short (0–3 months)
User Interaction | AI-U2 | Human Override Capability | Implemented | Govern / Manage | Hiring managers can override rankings; override tracking not logged | Lack of override audit trail may allow inconsistent decision-making | Log overrides with justification; review overrides quarterly for fairness trends | Medium | Medium (3–12 months)