## Sheet1
Control ID | Control Name | Domain | Status | Evidence / Notes | Key Risks if Not Implemented | Recommended Action | Priority | Target Timeline
A.5.1 | Policies for information security | Organizational | Partially Implemented | Policies exist in Confluence; no formal approval workflow; no evidence of annual review or version history retained. | Lack of consistency; failure to meet audit evidence requirements; unclear control ownership | Centralize policies in version-controlled repository (GitHub), establish ownership per domain, document approval workflow and implement annual review cadence aligned with release cycles. | High | Short (0–3 months)
A.5.7 | Threat intelligence | Organizational | Not Implemented | No process to track threat intel or integrate intel into risk assessments | Emerging threats targeting payroll and financial data may not be identified early, increasing likelihood of credential abuse or bank detail manipulation. | Subscribe to ISAC threat feeds (e.g., FS-ISAC), track indicators monthly, integrate findings into risk register and incident response playbooks. | Medium | Medium (3-12 months)
A.5.17 | Authentication information | Organizational | Implemented | MFA enforced for admin accounts via Okta; conditional access policies not applied consistently; exception handling informal. | Weak user authentication increases risk of account takeover & payroll manipulation | Extend MFA coverage to all privileged identities, enforce conditional access for high-risk sign-ins, and validate through quarterly access reviews with evidence logs. | High | Short (0-3 months)
A.5.21 | Data leakage prevention | Organizational | Not Implemented | No DLP monitoring on email or endpoints; no controls preventing unintentional export of payroll data; removable media unmanaged. | Sensitive data (PII, bank info) may be exfiltrated unintentionally or maliciously, leading to regulatory impact | Implement staged DLP controls beginning with outbound email scanning and endpoint restrictions for confidential data; integrate alerts with security operations workflow. | Medium | Long (12+ months)
A.6.3 | Information security awareness, education, and training | People | Partially Implemented | Annual training delivered but attendance untracked; no role-based modules for developers or support; phishing simulation absent. | Human error increases likelihood of credential compromise, fraud, and data leakage | Deploy tracked LMS with role-specific modules; run quarterly phishing simulations; report completion and risk reduction metrics to leadership. | Medium | Medium (3-12 months)
A.6.9 | Physical security monitoring | Physical | Implemented | CCTV and access logs retained; monitoring ad-hoc; no formal escalation path for anomalies. | Reduced visibility of unauthorized access attempts | Integrate physical access anomalies into incident response and correlate with logical access reviews. | Low | Long (12+ months)
A.7.2 | Physical entry | Physical | Partially Implemented | Badge access used for office entry; visitor logs inconsistent; badge deactivation not validated after role changes. | Unauthorized visitors may access support areas or devices containing customer data | Enforce visitor check-in with ID verification; implement quarterly badge access reviews and integrate with HR offboarding. | Medium | Medium (3-12 months)
A.8.16 | Monitoring activities | Technological | Not Implemented | CloudWatch collects logs but alerts not configured; no defined severity thresholds or triage procedure; logging gaps remain untracked. | Security incidents may go undetected, increasing impact duration & recovery cost | Define severity thresholds, implement alert triage workflow and response SLAs; integrate with SIEM or central monitoring platform and maintain audit evidence. | High | Short (0-3 months)
A.8.18 | Use of cryptography | Technological | Implemented | TLS enforced; encryption at rest via AWS KMS; key rotation policy exists but not validated | Weak encryption practices may expose customer data if misconfigured | Validate KMS key rotation annually and track exceptions; document cryptographic architecture; monitor for weak cipher suites and TLS deprecations. | Medium | Medium (3-12 months)
A.8.28 | Secure coding | Technological | Partially Implemented | CI pipeline scans code for vulnerabilities; results reviewed ad-hoc; no SDL defined | Code vulnerabilities may enter production, risking data exposure | Formalize secure development lifecycle (SSDLC) with mandatory security checks in CI, define remediation SLAs for critical vulnerabilities, and require signed code reviews for risk-sensitive components. | High | Medium (3-12 months)